## Seguimiento Por Empresa
HORAS ASIGNADAS VS HORAS EJECUTADAS POR EMPRESA
Row Labels | TIEMPO EJECUTADO [HRS] | ESTIMACION ASIGNADAS [HRS]
Deloitte SRL | 15.5 | 85
Dualbiz SRL | 22.5 | 64
Yimmys SRL | 1 | 110
Ysati Srl | 2.5 | 195
Grand Total | 41.5 | 454
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## asignacion
| SEGUIMIENTO DE ENGAGEMENTS | SEGUIMIENTO DE ENGAGEMENTS | SEGUIMIENTO DE ENGAGEMENTS | SEGUIMIENTO DE ENGAGEMENTS | SEGUIMIENTO DE ENGAGEMENTS | SEGUIMIENTO DE ENGAGEMENTS | SEGUIMIENTO DE ENGAGEMENTS
GENERADO POR: | BILLY CRESPO
FECHA REPORTE: | 24/08/2020
EMPRESA | ENGAGEMENT | FECHA INICIO | FECHA FIN | FACTURABLE | ESTIMACION TOTAL HORAS | HORAS OVERRUN | HORAS ASIGNADAS | EMPLEADO | HORAS EJECUTADAS
Dualbiz SRL | Contrato de Agosto 2020 | 2020-08-01 | 2020-08-31 | NO | 60 | 10 | 30 | Jorge | 10
Dualbiz SRL | Contrato de Agosto 2020 | 2020-08-01 | 2020-08-31 | NO | 60 | 10 | 4 | Alcides Yohacin | 0
Dualbiz SRL | Contrato de Agosto 2020 | 2020-08-01 | 2020-08-31 | NO | 60 | 10 | 30 | Kenji | 12.5
Ysati Srl | Engagement de prueba 1 | 2020-08-04 | 2020-08-12 | SI | 100 | 5 | 50 | Jorge | 0
Ysati Srl | Engagement para area contabilidad | 2020-08-04 | 2020-08-31 | NO | 40 | 0 | 20 | Kenji | 2.5
Ysati Srl | Engagement de prueba 4 | 2020-08-05 | 2020-08-12 | NO | 50 | 10 | 7 | Jorge | 0
Ysati Srl | Engagement de prueba 4 | 2020-08-05 | 2020-08-12 | NO | 50 | 10 | 20 | Alcides Yohacin | 0
Ysati Srl | Engagement de prueba 4 | 2020-08-05 | 2020-08-12 | NO | 50 | 10 | 30 | Kenji | 0
Ysati Srl | Engagement de prueba 4 | 2020-08-05 | 2020-08-12 | NO | 50 | 10 | 3 | Apaza Suntura, Edania Yoselin (LATCO - La Paz) | 0
Ysati Srl | Engagement de prueba 1 | 2020-08-04 | 2020-08-12 | SI | 100 | 5 | 45 | Alcides Yohacin | 0
Ysati Srl | Engagement para area contabilidad | 2020-08-04 | 2020-08-31 | NO | 40 | 0 | 20 | Alfaro Flores, Alicia Paola (LATCO - La Paz) | 0
Deloitte SRL | Contrato de Agosto para contadores | 2020-08-01 | 2020-08-31 | NO | 100 | 10 | 50 | Kenji | 15.5
Deloitte SRL | Engagement de prueba | 2020-08-15 | 2020-09-15 | NO | 50 | 10 | 25 | Arnold | 0
Deloitte SRL | Engagement de prueba | 2020-08-15 | 2020-09-15 | NO | 50 | 10 | 10 | Jorge | 0
Deloitte SRL | Contrato de Agosto para contadores | 2020-08-01 | 2020-08-31 | NO | 100 | 10 | 0 | Alcides Yohacin | 0
Yimmys SRL | contrato de agosto, para contadores | 2020-08-01 | 2020-08-31 | NO | 100 | 10 | 70 | Alcides Yohacin | 0
Yimmys SRL | contrato de agosto, para contadores | 2020-08-01 | 2020-08-31 | NO | 100 | 10 | 40 | Kenji | 1